## Phase3-TeamPlanning2023
CSI4142 - Project 2023
Phase 4 - Data Mining
Teamwork - breakdown of duties
Deliverable checklist | Responsible | Expected completion date | Actual completion date | Estimated | Actual | Notes (if any)
| team member(s) |  |  | time (hours) to complete | time (hours) to complete
Data preprocessing
Data summarisation | Alessandro, Arthur, Mershab | 2024-04-09 | 2024-04-09 | 5 | 10
.. Visualisation of attributes | Alessandro, Arthur, Mershab | 2024-04-10 | 2024-04-10 | 5 | 11
Data transformation | Alessandro, Arthur, Mershab | 2024-04-11 | 2024-04-11 | 5 | 12
.. Missing values | Alessandro, Arthur, Mershab | 2024-04-12 | 2024-04-12 | 5 | 6
.. Categorical data | Alessandro, Arthur, Mershab | 2024-04-13 | 2024-04-13 | 5 | 7
.. Numeric data | Alessandro, Arthur, Mershab | 2024-04-14 | 2024-04-14 | 5 | 7
.. Feature selection | Alessandro, Arthur, Mershab | 2024-04-15 | 2024-04-15 | 5 | 4
Data mining - Classification
Decision tree
Gradient Boosting
Random Forests
Comparison of results
Summary
Anomaly detection
One-class SVM
Summary
Other tasks - please specify